## Sheet1
Level | ID | Date | Milestone Title | Description
L3 | TE282 | 2020-12-07 | XoServe CCMT Relaunch | CCMT Relaunch complete including walkthrough of : 1) Approach to date 2) Defect management plan 3) Release Management plan 4) Partnering 5) Test schedule principles 6) Data provision 7) processes
L3 | TE285 | 2020-12-11 | XoServe RACi - industry sign off | Roles and Responsibilities for CCMT agreed : 1) all roles and responsibilities across all areas of CCMT have been defined 2) Roles and responsibilities signed off
L3 | TE284 | 2021-01-15 | XoServe Entry & Exit criteria agreed | Entry & Exit criteria complete including : 1) all criteria required by Xoserve to enter CCMT 2) all criteria required by market participants to enter CCMT 3) all criteria required by Xoserve to enable successful exit from CCMT 4) all criteria required by market participants to enable a successful exit 5) industry sign off of all criteria
L3 | TE283 | 2021-02-12 | XoServe Partnering Arrangments in place | Partnering arrangements complete. To include : 1) partnering principles 2) Partnering Approach 3) Partnering arrangements - industry sign off
L3 | TE286 | 2021-02-19 | XoServe Release Management Plan - Industry sign off | Release Management Plan complete: 1)Release Management plan review - industry review complete 2) Release management walkthrough complete 3) Release management plan - industry sign off
L3 | TE287 | 2021-02-26 | XoServe External Reporting pack agreed | External Reporting pack complete : 1) external reporting criteria defined 2) external reporting pack reviewed by industry 3) external reporting pack reviewed by Ofgem 4) External reporting pack - industry sign off
L3 | TE288 | 2021-03-05 | XoServe CCMT Approach - Industry sign off | Test Approach completed. This document will include the following for the test phase: 1) Detailed Approach to all areas of the test phase 2) Connectivity testing 3) Agreed list of test processes 4) Entry & Exit processes 5) Test phase responsibilities 6)Test Data provision 7)Release Management strategy 8) Defect management strategy 9) Test Reporting 10)Partnering Arrangements 11)Registration arrangements 12) System connection & API Registration Approach
L3 | TE265 | 2021-03-12 | Xoserve consequential systems change test preparation complete | All preparation activities as agreed within the Xoserve CCMT Approach document are complete . This includes the production and sign-off of the following documents by Xoserve and members of the CCMTWG( Consequential Change Market Trials Workgroup) 1) Test approach 2) Test processes 3) Test data requirements 4) data provision 5) Defect management plan 6) Release Management plan
L3 | TE289 | 2021-03-12 | XoServe G0/No Go decision | GNG complete : 1) all GNG criteria agreed 2) GNG schedule in place 3) GNG decision taken
L2 | TE270 | 2021-04-12 | Xoserve consequential systems change test window starts | This testing with Xoserve will involve all participants in order to prove the Xoserve changes. Xoserve make consequential changes to UKLink, DES and Gemini available for shippers, GTs and iGTs to test
L2 | TE280 | 2021-11-05 | Xoserve consequential systems change test window ends | This testing with Xoserve will involve a set of participants in order to prove the Xoserve changes. Xoserve make consequential changes to UKLink, DES and Gemini available for shippers, GTs and iGTs to voluntarily test Progress reports to be submitted to Ofgem throughout the test phase and decisions made 2 weeks prior to the end of the phase regarding the utilisation of the contingency period