## Sheet1
Date Raised | Issue Title | Issue Summary | Latest Update | Communication Reference | Impact | Action Plan & progress | Customers Impacted | Expected Resolution Date | Status | Resolution | Resolved Date
2024-01-01 | DDP data issues | Data displayed & reported via DDP not correct. Meter Points captured in the AQ Read Performance Dashboarding had accepted reads within the expected time standard and so should not be included.​ | Options have been explored and an approach has been agreed. Fix to be implemented and deployed by mid – May.​ |  | This means that read performance as analysed by the Performance Assurance Committee is understated and will not reflect Shippers’ actual read performance.​ No impact to Settlement processes. | Apply fix mid-May 2024. | Shippers | Mid May 24 | In progress
2024-04-11 | Duplicate SC9 files issued to you today in error | Duplicate SC9 files have been sent to customers on 11 April 2024. These files were sent to you previously on 2 February 2024 and should be deleted | Communication issued to all impacted customers on 11 April 24 | XCE2022 | Duplicate SC( files sent morning of 11 April 24. | Notify impacted customers. | All | 2024-04-11 | Closed | SC9 files were being used for testing but were loaded into production in error. Further checks implemented to ensure this is not repeated with any testing files. | 2024-04-11
2024-03-01 | Commodity Invoice Issued with Incorrect Values | The aggregated Commodity invoice value for the February 2024 billing period was incorrect. This has impacted 18 Shippers for 2 Networks. | Adjustments were issued to impacted Shippers on 21 March 2024 & 2 impacted DNs notified of adjustment values. | XCE2021 | Incorrect aggregated on the February 2024 Commodity invoice. | Root cause analysis has identified this was due to a manual error during pre-billing checks. Further training has been carried out & a senior team member will carry out checks on any charges reversed & re-billed. | Shippers DNs | 2024-03-21 | Closed | Further checks implemented | 2024-03-21
2024-03-01 | Incorrect settlement data issued to Electricity SwitchStream customers | For pending switches with an effective date of 1 April 2024, the incorrect date is being issued within the 137 record, of the 058 file (field ‘EFFECTIVE_TO_SETTLEMENT_DATE{REGI}_FOR_OLD_SUPPLIER‘) | Fix has been successfully implemented on 8 March 24 and quality assurance checks have confirmed that the correct settlement end date is now being issued on all D0058 file flows. | XCE2020 | If the outgoing Supplier automatically objects to a switch (due to the incorrect settlement data), the switch will be cancelled, and the Supply Meter Point will remain with the existing Supplier. As a result, this has the potential to impact Electricity Option 2 gaining Suppliers. | Issue due to summertime change in March 24. A fix has been implemented to ensure no further occurances. | Electricity Suppliers | 2024-03-08 | Closed | Fix implemented | 2024-03-08
2024-02-01 | Shipper registration not recorded on UKLink | On 13 February 2024, the Central Switching Operator notified the CDSP of new registrations to become effective on 14 February 2024. For 139 MPRNs, the registrations were not actioned in UKLink | The registration will be processed in UKLink on 23 February 2024 with an effective registration effective date of 24 February 2024 | XCE2019 | In CSS systems, the Supplier will be registered at the MPRN on 14 February 2024. The Shipper registration effective date in UKLink is 24 February 2024. There is a misalignment in Supplier(in CSS systems) and Shipper (in UKLink) registration effective dates for the 139 impacted MPRNs. | The registration will be processed in UKLink on 23 February 2024 with an effective registration effective date of 24 February 2024 | Shippers | 2024-02-24 | Closed | Shipper registration processed in UKLink on 24 February 2024 | 2024-02-24
2024-02-01 | Estimated Shipper Transfer Meter Reading not Calculated | From July 2023, an estimated Shipper transfer meter reading for the registration effective date has not been calculated, recorded in UKLink or sent to Shippers | Communication issued to impacted Shippers on 14 February 2024 notifying of the issue and data set of impacted MPRNs. | XCE2017 | An estimated transfer meter reading has not been calculated and sent to both incoming & outgoing Shipper. | Calculate the transfer meter reading & submit to Shippers. Root cause identified a defect for a specific scenario impacting a small number of MPRNs, fix applied on Wednesday 10 April 24. Communication issued to all impacted customers. | Shippers | 2024-03-01 | Closed | Fix applied 10 April 24 | 2024-04-10
2024-01-12 | Delay in submitting .CZI file to Shippers | Delay in submitting the CORE CAPACITY INDIVIDUAL SMP SUPPORTING INFORMATION (.CZI) file | Communication issued 12 January notifying of the delay and on 15 January 2024 advising Shippers that the files were issued on 14 January 2024. | XCE2016 | Delay for customer who have requested the supporting information file. | Submit the files. | Shippers | 2024-01-14 | Closed | Submit files | 2024-01-14
2024-01-01 | Meter Readings incorrectly rejected | Class 3 and 4 meter readings were not processed due to batch job failures during December 2023 & January 2024. | Communications issued dueing January providing customers with update and data set of impacted MPRNs. | XCE2015 | Meter readings not fully processed & Shipper received rejection notification. | Re-processed all meter readings on the 9th & 10 January 2024. , The meter readings will be considered for downstream processes; AQ, Reconciliation & performance reporting | Shippers | 2024-01-10 | Closed | All meter readings processed. | 2024-01-10
2023-10-01 | Incomplete data issued in TMC file | A TRANSFER AND METER READ COMBINED (.TMC) file was issued notifying Shipper of the registration of MPRNs with an effective date of 27 October 2023. The file contained records for 57 MPRNs where the AQ was blank | Communication issues 27 October 2023. | XCE2013 | Incomplete data submitted to the Shipper in the .TMC file. AQ missing from the file. | Communication issued requesting Shippers preference for resolving the issue for them | Shipper | 2023-10-31 | Closed | Shippers preferred option actioned. | 2023-10-31
2023-09-01 | Unprocessed BRN and SPC files | Base Registration Notification (BRN) and Supply Meter Point Amendment (SPC) files have not been processed | Communication issued 20 September 2023 advising actions required to take. | XCE2012 | For any unprocessed BRN files, default settlement values will have been applied to the Supply Meter Point(s) in UK Link. For any unprocessed SPC files, requested amendments to Supply Meter Point(s) have not been applied to UK Link. | Complete root cause analysis & apply enduring fix. | Shippers | 2023-09-01 | Closed | Fix implemented & Shippers advised of correction actions required. | 2023-09-01
2023-07-01 | Replacement reads rejected incorrectly | Following implementation of XRN5091 on 24 July 2023, it was identified that a replacement meter reading was incorrectly rejected in UK Link. | Communication issued on 24 July to all impacted Shippers providing affected MPRNs. | XCE2010 | Replacement meter reading rejected | Fix implemented & Shippers advised to re-submit their meter readings. | Shippers | 2023-07-19 | Closed | Fix implemented & Shippers advised to re-submit their meter readings. | 2023-07-19
2023-07-01 | Opening Meter Readings Rejected | Opening Transfer and Class change meter readings rejected in error. The meter readings are being rejected for a certain scenario whereby there is a Shipper transfer on a class 3 or a shipper transfer with Class change from Class 4 to Class 3. | Enduring fix deployed on Wednesday 19 July 2023. Opening meter reading recorded in UKLink and a notification submitted of the meter reading to both the outgoing and incoming Shippers | XCE2008 | Opening Shipper transfer meter readings submitted by the Incoming Shipper have been incorrectly rejected | Fix deployed on 19 July 23 and opening meer readings re-processed. | Shippers | 2023-07-20 | Closed | Fix deployed on 19 July 23 and opening meer readings re-processed. | 2023-07-20
2023-07-01 | Significant LDZ Input Measurement Error | Offtake meter in LDZ EM has been under-recorded from 01/04/2022 to 31/07/22. Approximate impact of 790 GWh for the period (as published on the Measurement Error Register). | Communication issues 29 June 2023 (XCE2004) | XCE2004 email communication & update provided to CoMC | The total energy recorded as being delivered into the LDZ is incorrect for the period. Unidentified Gas (UIG) is incorrect in the affected LDZ. When the error is corrected this will result in charges to all Gas Shippers with a live meter point portfolio in the affected LDZs during the affected period | 1. The error will be assessed by the independent expert, and their report has been presented at Offtake Arrangements Workgroup, 2. Once completed, Xoserve will process the correction as UIG Reconciliation on the Amendment Invoice. | Shippers |  | Closed | Adjustments issued on the July Amendment invoice | 2023-07-01
2023-07-06 | Missing Messages | Following the implementation of the Central Switching Service (CSS) in July 2022, there have been Registrations where the UK Link system has not received the Registration notification from CSS | Following a CSS PI major Incident identified on 6 July 2023, there were circa. 84k gas registrations that did not become effective on the expected date. From 2 August 2023, CSS started to progress the missed registrations, with the original effective date. This activity completed on 7 August 2023 although 24 remain outstanding. Impact of this will be a misalignment between that CSS systems (record the original registration effective date) and gas settlement systems (prospective registration effective date). | XCE2006 | 1. UKLink will be out of sync with the CSS system as the Outgoing Shipper/Supplier will still be recorded at the Supply Meter Point on UKLink. 2. Transportation and energy charges will continue to be applied to the Outgoing Shipper until records have been updated. 3. Transportation and energy charges have not been applied to the Incoming Shipper. 4. Any changes associated with the switch have not been actioned e.g., Class change, contact data change. 5. Any transactions submitted by the Incoming Shipper since the switch effective date may have been rejected e.g. meter reads, asset updates etc. 6. Any transactions submitted by the Outgoing Shipper since the switch effective date may have been accepted e.g. meter reads, asset updates etc 7. Reporting, DDP, GES and portfolio files will show the incorrect Shipper registered at a Supply Meter Point | 1. Following approval of Mod 0855, progress financial adjustments & communicate to impacted Shippers that the meter reading for CSS registration effective date can be replaced. 2. Develop run-book with customers for potential future scenarios and the required actions parties need to take. 3. Modifications approved, implementation date to be determined. Once implemented, meter readings will be loaded into UKLink & financial adjustments assessed. | Shippers DNs IGTs | November 2023 (Mod approval). Continue until a process has been implemented to manage missing messages | In progress
2023-05-01 | Winter Consumption Calculation | The Winter Consumption (WC) calculation for 2,149 MPRNs across the industry is overstated. These values are issued in the May AQ WC Notification | Communication issued 3 July 2023 (XCE2005) to Contract Managers providing their impacted MPRNs. | XCE2005 email communication & update provided to CoMC | Incorrect WAR band assigned meaning Supply Offtake Quantity (SOQ) values sent in September’s .NRL files (to be effective 1 October 2023) will potentially be incorrect | 1. For the impacted MPRNs, Shippers were asked to raise a Winter Consumption correction via the AQ Correction (AQI) file to apply or amend the proposed WC value 3. Communication issued to Shippers on 3 July 2023 providing impacted MPRNs & actions that will be undertaken & required by Shippers and a further communication issued on 8 August 2023 providing re-calculated values for Shippers to review 3. Change Requests raised to implement a fix prior to the run in May 2024 | Shippers DNs | 2024-05-01 | Closed | Communications issued to impacted customers, deadline date to submit updates to WC was mid September, values went live on 1 October 2023. Change Proposal will be tracked for implementation prior to March 2024. | 2023-09-01
2023-03-20 | MPRNs Sent to Shippers in Error | MPRN(s) have been sent to Shippers in error on the Transfer and Meter Read Combined file (.TMC). | Communication issued to impacted customers on 20 March 2023 | XCE2001 | Shippers have received MPRN(s) not in their ownership in the S88 record on the TMC file. Only the MPRN in the S88 record was incorrect. The remaining data within the TMC file is also correct | Until a fix has been implemented, if files are held, checks will be put in place when releasing the files | Shippers | TBC | Closed | Fix implemented | 2023-05-01
2023-02-07 | SwitchStream issue | Between 26 – 31 January 2023, there was an issue with the SwitchStream service, which resulted in a small number of erroneous Shipper transfers | Communication issued to impacted customers on 7 February 2023 | XCE1998 | The Shipper who was in ownership of the Supply Meter Points at the time did not receive The ‘Invitation to Intervene’ notification (CFR S10 withdrawal notice), and was therefore unable to object to the pending registrations. | Notification to Shippers impacted (outgoing and Incoming) advising of further action required. | Shippers DNs IGTs | N/A | Closed | Actions taken by impacted Shippers. | 2023-03-01
2022-10-01 | Consumer contact data | Consumer contact data provided by Shippers is not complete when sent in the daily/quarterly portfolio files to IGTs & DNs | Defect raised and is being progressed. All consumer data is being checked on quarterly (IQL) file. For completeness, the DNs portfolio report is also being reviewed (EDL & EQL) -Report providing all consumer contact data sent January 23 following IQL submission -Checks performed have confirmed IDL report is correct and complete | Updates provided at CoMC and Customer Constituency meetings | Incomplete data sent to IGTs and DNs on their portfolio files | 1. Defect raised and is being progressed. Identify Issue and root cause - main issue due to the ‘special characters’. Fix has been applied. 3. An ad-hoc report of the quarterly portfolio file will be created to carry out further checks to identify any further issues. 4. Further fixes due to be implemented by 20 October and an ad-hoc report issued to customers who have requested it w/c/ 23 October 2023. 5. Final data issue will be resolved prior to files being issued in April 2024. | IGTs DNs | 2024-04-01 | Closed | Fix applied to all identified issues. Quarterly portfolio files sucessfully issued over weekend of 20/21 April 24 | 2024-04-22
| Defects impacting the AQ calculation | 5 AQ impacting defects (defects impacting AQ calculation) as at 2 July 2023 | Update provided to monthly Contract Management Committee (CoMC) meetings | Updates provided at CoMC | Incorrect transportation rates applied to charges Over/under allocation of energy for demand estimation processes, impacts to UIG | 1. Profiling carried out to identify impacted MPRNs 2. AQs are corrected to limit impact on the customer. 3. All profiled sites for outstanding AQ calculation impacting defects have been corrected along with the new Formula Year | Shippers DNs IGTs | Managed as part of CoMC updates | Closed | Agreed at September CoMC this can be closed as no. of defects reduced to 3. This will be managed as BAU. | 2023-09-01
2020 | Defects impacting the charges issued on the Amendment invoice | 3 open defects impacting the Amendment invoice (reconciliation charges) as at 2 July 2023 | Update provided to monthly Contract Management Committee (CoMC) meetings | Updates provided at CoMC | Reconciliation charges are incorrect if defect is not identified prior to invoice issue Reconciliation charges are held until the defect is fixed and data corrected | 1. Profiling carried out monthly to identify impacted MPRNs 2. Charges for impacted MPRNs are held and not invoiced until the fix is deployed and energy is corrected, where required, prior to the charges being released | Shippers DNs | Managed as part of CoMC updates | Closed | Agreed at May CoMC this can be closed as no. of defects reduced to 3. This will be managed as BAU. | 2023-05-01