## Sheet1
Scenario No. | Defect No | Impact to AQ? | Process Area | MPRN's | Consumption Adjustment Approach | Billed and Excluded profile dates | Datafix Build date | Testing Completion Date | AT completion date | Script implementation date | Correction Completion date | Billing Month
49 | 720 | No | Prime and Sub reads |  | NA | NA | NA | NA | NA | NA | NA
A12 | 914 | Yes | Transfer Read | 5700 | No | 2018-12-14 | POC - 12/12/2018 | 2018-12-28 | NA | NA | 2019-01-15 | Jan Billing
A21 | 945 | Yes | MR07 Exception Resolution | 19 | Yes | 2018-12-14 | 2018-12-14 | 2019-01-05 | 2019-01-15 | 2019-01-25 | 2019-02-05 | Jan Billing
A22 | 1045 | Yes | Replacement Reads | 809 | No | 2018-12-14 | 2019-01-18 | 2019-02-08 | 2019-02-15 | 2019-02-20 | 2019-02-27 | Feb Billing
A15 | 1052 | Yes | UMR reads | 642 | Yes | 2018-12-14 | 2018-12-14 | 2019-01-05 | 2019-01-15 | 2019-01-25 | 2019-02-05 | Jan Billing
72/73 | 947 | Yes | Nomal read processing | 1808 | Yes | 2018-12-14 | 2018-12-14 | 2019-01-05 | 2019-01-15 | 2019-01-25 | 2019-02-05 | Jan Billing
67 | 837 | No | Class change read | 2567 | No | 2018-12-14 | NA | NA | NA | 2019-01-07 | 2019-01-09 | Dec Billing month
61 | 881 | No | Replacement Reads | 45 | Yes | 2018-12-14 | 2018-12-14 | 2019-01-05 | 2019-01-15 | 2019-01-25 | 2019-02-05 | Jan Billing
23/51 | 727 | No | Consumption Adjustment | n/a | Yes | 2018-12-14 | 2018-12-14 | 2019-01-05 | 2019-01-15 | 2019-01-25 | 2019-02-05 | Jan Billing
45 | 747 | Yes | Site visit Reads | 200 | No | 2018-12-14 | 2019-01-18 | 2019-02-08 | 2019-02-15 | 2019-02-20 | 2019-02-27 | Feb Billing
74 | 933 | Yes | Normal Read |  | NA | 2018-12-14 | NA | NA | NA | NA | NA
16 | 881 | No | Replacement Reads | 4611 | Yes | 2018-12-14 | 2018-12-14 | 2019-01-05 | 2019-01-15 | 2019-01-25 | 2019-02-05 | Jan Billing
39 | 631 | No | RGMA Reads | n/a | No | 2018-12-14 | NA | NA | NA | NA | NA