## Slide 1: DSC Delivery Sub-Group
1st April 2019

## Slide 2: Agenda (1)
Item | Title | Document Ref | Lead | Action Required From DSG
1. | Welcome and Introductions | Verbal | Chair | Introduce yourself
2. | Meeting Minutes | Verbal | Chair | Approval of the meeting minutes for the previous meeting
3. | Defects |  |  | 
3a. | AQ Defects | Spreadsheet published on Xoserve.com | Eamonn Darcy | Standing agenda item – for information (if there is an update)
3b. | Defect Dashboard | Slides Only | Mark Tullett | Standing agenda item – for information (if there is an update)
4. | Portfolio Delivery |  |  | 
4a. | Portfolio Overview POAP | POAP published on Xoserve.com |  | Standing agenda item – for information (if there is an update)
4b. | Retail and Network Delivery Overview | Slides only | Richard Hadfield/Julie Bretherton | Standing agenda item – for information – no update
5. | Release Update |  |  | 
5a. | Release 3 | Slides Only | Tom Lineham | Standing agenda item – for information – no update
5a. | Minor Release Drop 3 | Slides Only | Matt Rider | Standing agenda item – for information (if there is an update)
5b. | June 19 | Slides Only | Tara Ross | Standing agenda item – for information (if there is an update)
5c. | End User Categories 19 | Slides Only | Matt Rider | Standing agenda item – for information (if there is an update)
5d. | November 19 | Slides Only | Tom Lineham | Standing agenda item – for information (if there is an update)
6. | New Change Proposals For Ratification of the Prioritisation Scores |  |  | 

## Slide 3: Agenda (2)
Item | Title | Document Ref | Lead | Action Required From DSG
7. | Change Proposal Initial View Representations |  |  | 
7a. | XRN4871 - Modification 0665 – Changes to Ratchet Regime | Slides Only | David Addison / Ellie Rogers | None – For Information and discussion
7b. | XRN4645 - The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Slides Only | David Addison | None – For Information and discussion
7c. | XRN4780 - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | Slides Only | David Addison / Simon Harris | None – For Information and discussion
7d. | Reporting XRN delivery recommendations | Slides Only | Jane Goodes | DSG action to approve solution option.
8. | Undergoing Solution Options Impact Assessment Review |  |  | 
8a. | XRN4833 - Roll Out of Business Intelligence and Data Discovery Capability | Verbal Update | Jason McLeod | None – For Information and discussion
9. | Solution Options Impact Assessment Review Completed |  |  | 
9a. | XRN4713 - Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | Slides Only | Simon Harris | None – For Information and discussion
9b. | XRN4803 - Removal of validation for AQ Correction Reason 4 | Slides Only | Emma Smith | None – For Information and discussion
10. | Miscellaneous |  |  | 
10a. | XRN4777 – Acceptance of contact details updates | Slides Only | Emma Smith | DSG action to approve progression on current design
11. | JMDG Update | Slides Only | Simon Harris | None – For Information and discussion
12. | Action Updates | Action log to be published on Xoserve.com | All | Updates required on DSG owned actions (see below)
13. | AOB | Slides Only | Various | TBC
13a. | Website Update – Change Packs and Change Proposals. | Slides Only | Richard Johnson | None – For Information and discussion

## Slide 4: 3. Defects update
3a. AQ Defects
3b. Defect dashboard

## Slide 5: 3a. AQ Defects
The AQ Defects spreadsheet is saved in the DSG pages on xoserve.com listed as 3a. AQ Defects

## Slide 6
3b. Defect Summary

## Slide 7: Defect Summary Stats
Stats as per HPQC extract taken on Wednesday 27th March 2019.
Defect Landscape (Open/Closed vrs PGL/New) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | PGL Defects |  |  |  |  |  | Newly Discovered Defects |  |  |  |  |  |  | GRAND RELEASE TOTALS
 | D1 | D2 | D3 | D4 | D5 | TOTAL | D1 | D2 | D3 | D4 | D5 | Not Set | TOTAL | 
Urgent Fix (D1/D2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 7 | 7
Amendment Invoice Task Force | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 1 | 4 | 18 | 18
R3.10 - 5th April | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6 | 0 | 0 | 16 | 16
On Hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Requires CR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 4 | 4
Release Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1
Future Release Dependent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Currently Unallocated | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 12 | 25 | 0 | 0 | 37 | 39
TOTAL OPEN | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 38 | 40 | 1 | 4 | 83 | 85
Closed as Rejected | 0 | 0 | 3 | 14 | 6 | 23 | 0 | 11 | 45 | 41 | 1 | 3 | 101 | 124
Closed as CR | 0 | 0 | 3 | 8 | 0 | 11 | 0 | 0 | 6 | 5 | 0 | 0 | 11 | 22
Closed - Deployed to Production | 0 | 7 | 28 | 58 | 9 | 102 | 9 | 213 | 461 | 217 | 14 | 10 | 924 | 1026
TOTAL CLOSED | 0 | 7 | 34 | 80 | 15 | 136 | 9 | 224 | 512 | 263 | 15 | 13 | 1036 | 1172
GRAND TOTAL | 0 | 7 | 31 | 73 | 16 | 138 | 9 | 224 | 544 | 298 | 16 | 17 | 1119 | 1257

## Slide 8: R3.09
The below fixes were all deployed to production between the 1st and 8th March.
Release 3.10 is scheduled for 5th April 2019.
The below fix was deployed as urgent.
Defect ID | Status | Description | Release
1105 | Closed - Deployed to Production | Linked with 1247 task force defect SAP ISU AQ- Winter Consumption calculation process is populating the ‘Status of the record in May’ for failure Reason Code WTC00028 as blank but it should be populated with 'F' as failed. | R3.09
1162 | Closed - Deployed to Production | SAP - UPI (User Pays Index) File Name not incrementing | R3.09
1200 | Closed - Deployed to Production | UKLink (SAP ISU) -SPA : RFA request is incorrectly getting rejected | R3.09
1211 | Closed - Deployed to Production | SAP- supplier short code not getting populated in ZCS and COM file for SSMP | R3.09
1264 | Closed - Deployed to Production | SAP AQ-Incorrect EUC number, description and Confirmation reference number populated in the T98 record of the AQ notification. | R3.09
1286 | Closed - Deployed to Production | Invoices related to any gemini info type | R3.09
1302 | Closed - Deployed to Production | Topic CONFIRM_NO_ASSET | R3.09
1306 | Closed - Deployed to Production | SAP BW- Last inspection date is missing in 0ucinstalla for all the records. | R3.09
1307 | Closed - Deployed to Production | Meter Asset History Tab in DES showing Corrected and Uncorrected Reads incorrectly. | R3.09
Defect ID | Status | Description | Date
1320 | Closed - Deployed to Production | SAP - EXZ file sent to shipper where confirmation was lapsed and offer was not valid | 16th March

## Slide 9: Amendment Invoice Impacting Defects
Key: | 
 | Amendment Invoice Task Force Defects
 | Standard Defect
Defect ID | Status | Primary Business Process | Description
1122 | Clarification Required | READS | Multiple RGMA reads (Final Exchange and Report read) present in the system for the same day leading to incorrect one day rec.
1173 | Fix In Progress | INV | Mismatch in ASP file & not captured in mismatch report where legacy data used for Rec
1178 | Awaiting CAB | RGMA | Linked with 1290,789 and 1309 ASP/AML mismatches when Class 4 read is received for the same read date as RGMA read.(creates MR07 exception)
1199 | Ready For Assurance | READS | Volume and energy calculated wrong where Read insert between actual and estimated shipper transfer with TTZ of 1 (inseted using manual read screen). Affects AQ & charge calculation for Amendment invoice
1207 | Ready For Assurance | RGMA | SAP - Incorrect volume being calculated for Class change scenario for Class 1 site
1218 | Clarification Required | READS | Incorrect energy calculated: Treatment of Check to Check Reconciliation spanning across Classes
1219 | Clarification Required | READS | SAP: Issue with DM Estimation following RGMA update for CA/CL site: Potential charge issue.
1278 | Ready For Assurance | READS | Better Estimate on Twin stream sites does not seem to be allocated aggregate energy correctly
1308 | Assigned | INV | SAP- where a reconciliation covers pre go live period the original vairances are created manually causing mismatch issues.
1314 | Assigned | INV | SAP - Incorrect Netting off seen within ASP files when there are multiple re-recs within same month for the same REC period
1315 | Assigned | INV | SAP- Enduring fix on the Amendment Invoice to stop manual workaround to prevent pre LiS charges being included on the invoice.
1318 | Fix In Progress | INV | Energy does not equal financial charge on the Amendment Invoice
1321 | DRS Needed | SPA | Volume not calculated correctly when Class 4 (via UMR) read is suppressed by asset update (FINC) read causing 1 day rec.
1324 | DRS Needed | INV | SAP - AML presentation issue
1331 | New | READS | DM prime REC charges are not getting calculated & presented within ASP supporting information file
1332 | New | READS | ASP batch: Charges not presented within ASP file as the batch process is doing a lookup into the REC interface tables with a different REC end date (30.11.18) to the actual REC date (02.12.18)
1333 | New | READS | Analysis of the interface between billing and DM REC to avoid financial mismatches (Sc52)
1334 | New | READS | Two Inflight RECs processed within D+5 close out are identified to have an inconsistency in terms of mapping the GUID and the REC start/end dates

## Slide 10: Amendment Invoice Impacting Defects - Closed
The below defects were deployed / closed since the last slides were issued.
Key: | 
 | Amendment Invoice Task Force Defects
 | Standard Defect
Defect ID | Status | Description | Dep/ Close Date
1247 | Closed - Deployed to Production | Linked with 1105 WC calculation process incorrectly rejecting & resulting in incorrect volume & energy calculated. Charges Excluded from invoice. | 22nd March
1249 | Closed - Deployed to Production | SAP - Incorrect values in Supporting Info (ASP & AML) for CSEPs, not showing FYAQ | 22nd March
1252 | Closed - Deployed to Production | Missing reconciliation data missing in ASP file for record type K89 | 22nd March
1262 | Closed - Deployed to Production | SAP-SSMP presentation issue in the ASP file. | 22nd March

## Slide 11: 4. Portfolio Delivery Overview POAP
4a. The Portfolio POAP is saved in the DSG pages on xoserve.com listed as 4. Portfolio Overview POAP
4b. Retail and Network Delivery Overview

## Slide 12: R&N Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2019 | 2020
June-19
Sept-19 (EUC)
Nov-19
CSS CC
RETRO
UIG
Mod 678 – GB Charging
Feb-20
June-20
Nov-20
Assumes February Release continue to be documentation only release
Assumes RETRO will be Nov 2020 Major Release Delivery
Please note that this is all potential activity within UK Link over the next 24 months
Minor Release D4

## Slide 13: 2019 / 2020 R&N Delivery Timeline
2019 | 2020
Assumes February Release continue to be documentation only release
Assumes RETRO will be Nov 2020 Major Release Delivery
Please note that this is all potential activity within UK Link over the next 24 months
Jun-19
Build
Testing
Imp
PIS
EUC
Build
Testing
Imp #1
PIS
Imp #2
PIS
Nov-19
Capture
Initiation
Design
Build & UT
ST
SIT
UAT
Reg / Pen Test
Imp
PIS
MT
MR
Potential Activity
CSS CC
HLD
Detailed Design
System / Internal Acceptance / Pen Testing
SIT / Reg Test
MT
IMP
Retro
Nov-2020
UIG
2020
ST
SIT
SUPT
UKL PT
UKL ST
UKL AT & RT
UT
UKL RT
UAT
IDR
IMP
PIS
Mod678 – Uk Link Impacts
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
J | F | M | A | M | J | J | A | S | O | N | D

## Slide 14: 2019 / 2020 R&N Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2019 | 2020
Assumes February Release continue to be documentation only release
Assumes RETRO will be Nov 2020 Major Release Delivery
Please note that this is all potential activity within UK Link over the next 24 months
Jun-19
BER Approval 09/01/19
Sep-19 / EUC
BER Approval 09/01/19
Nov-19
BER Approval
10/04/18
EQR Approval
06/02/19
Change Pack Issue
08/05/19
MR
Potential Activity
ChMC Scope Approval
10/04/19
RETRO
Potential Activity
Governance Approval dates tbc
On track
At risk
Key
Complete
Feb-20
Potential Activity
Governance Approval dates tbc
BER Approval
10/04/19

## Slide 15: Change Index – R&N Allocated Change
Proposed Release | XRN | Change Title | Current Status | Xos Proposed Prioritsation Score | Proposed R&N Release | Complexity | Finance
June 19 | 4670 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | In Delivery | 27% | June 2019 | Low | Xoserve
 | 4687 | PSR updates for large domestic sites | In Delivery | 37% | June 2019 | Low | Shippers
 | 4676 | Reconciliation issues with reads recorded between D-1 to D-5. | In Delivery | 67% | June 2019 | Medium | Xoserve
Sept 19 | 4376 | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | In Delivery | 31% | September 2019 | High | NTS
 | 4665 | Creation of new End User Categories | In Delivery | 52% | June/Sep-2019 | High | Shippers
Nov-19 | 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | CP high level solution approved at ChMC | 41% | November 2019 | Medium | Xoserve
 | 4725 | New read reason type for LIS estimate readings | CP high level solution approved at ChMC | 28% | November 2019 | Medium | Xoserve
 | 4621 | Suspension of the validation between meter index and unconverted index | CP high level solution approved at ChMC | 29% | November 2019 | Tbc | Shipper

## Slide 16: Change Index – R&N Unallocated External Impacting Changes
Proposed Release | XRN | Change Title | Current Status | Xos Proposed Prioritsation Score | Indicative R&N Release | Complexity | Finance
Unallocated | 4777 | Acceptance of Contact Details Updates | A7 - CP awaiting ChMC solution approval | 32% | Minor Release Drop 4 | Tbc | Shippers
 | 4795 | Amendments to the PARR (520a) reporting |  | 44% | Minor Release Drop 4 | Tbc | PAC
 | 4780 | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | A7 - CP awaiting ChMC solution approval | 27% | Minor Release Drop 4 | Tbc | Tbc
 | 4803 | Removal of validation for AQ Correction Reason 4 | A7 - CP awaiting ChMC solution approval | 71% | Minor Release Drop 4 | Tbc | Shippers
 | 4871 | Modification 0665 – Changes to Ratchet Regime | A2 - CP proposed for ChMC | 27% | Minor Release Drop 4 | Tbc | Tbc
 | 4866 | UIG Recommendation – removal of validation on uncorrected read | A2 - CP proposed for ChMC | 28% | Nov-19 | Tbc | Tbc
 | 4851 | Moving Market Participant Ownership from SPAA to UNC/DSC | A5 - CP in capture with DSG | 47% | Feb 2020 | Tbc | Tbc
 | 4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | A5a - Solution Development | 44% | June 2020 | Tbc | Shippers/DN
 | 4772 | Composite Weather Variable (CWV) Improvements | A7 - CP awaiting ChMC solution approval | 44% | June 2020 | Tbc | Shippers / DN
 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | A2 - CP proposed for ChMC | 41% | June 2020 | Tbc | Tbc
 | 4850 | Notification of Customer Contact Details to Transporters | A2 - CP proposed for ChMC | 33% | June 2020 | Tbc | Tbc
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | A2 - CP proposed for ChMC | 32% | June 2020 | tbc | tbc
 | 4801 | Additional information to be made viewable on DES | A5 - CP in capture with DSG | 29% | June 2020 | Tbc | Tbc
 | 4716 | Increased Field Length – ‘Updated by’ data item | A5b - Undergoing Solution Impact Assessment | 9% | Minor Release Drop 5 – 2020 | Tbc | Tbc
 | 4896 | Failure to Supply Gas System and Template Amendment | A9 - Internal change progressing through capture | 25% | Minor Release Drop 5 – 2020 | Tbc | Tbc
 | 4897 | Resolution of deleted Contact Details (contained within the S66 records) at a Change of Shipper event | A9 - Internal change progressing through capture | 37% | Minor Release Drop 5 – 2020 | Tbc | Tbc
 | 4899 | Treatment of Priority Service Register Data and Contact Details on a Change of Supplier Event | A5 - CP in capture with DSG | 22% | Minor Release Drop 5 – 2020 | Tbc | Tbc
 | 4474 | Delivery of Retro | A9 - Internal change progressing through capture | 48% | 2020 | Tbc | DN
 | 4584 | Central Switching Services | A9 - Internal change progressing through capture | 20% | 2020 | Tbc | Shippers
 | 4627 | Consequential Central Switching Services | B1 - Start Up In Progress (Awaiting PAT/RACI) | 51% | 2020 | Tbc | Shippers
 | 4854 | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | A5 - CP in capture with DSG | 29% | Unallocated | Tbc | Tbc
 | 4713 | Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | A5b - Undergoing Solution Impact Assessment | 32% | Unallocated | Tbc | Shippers

## Slide 17: 5. Major Release Update
5a. Release 3
5b. Minor Release Drop 3
5c. June 2019
5d. EUC 2019
5e. November 19

## Slide 18: 5a. XRN4572 UK Link Release 3
1st April 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Track 1 (13 Changes) & Track 2 (XRN 4454 Cadent/ NG) – Implemented. PIS Complete Project Closure Report to be issued to ChMC in April |  |  | 
Risks and Issues | Issue against XRN 4534 RGMA Validation Rules (Unable to Implement in Track 1) Implemented and PIS concluded in March |  |  | 
Cost | Full Delivery costs approved at ChMC in April 2018. Revision to accommodate XRN4454 (Cadent) delivery approved at December ChMC. |  |  | 
Resources | Delivery and PIS completed. No further resource requirements to support R3 with exception of PM to document closure report |  |  | 

## Slide 19: UK Link Release 3 - Plan
Primary Scope | Scoping |  |  | Initiation |  | Delivery |  |  |  |  |  | Realisation | 
Stage | Scope Prioritisation | Scope Defined | Funding | Initiation | Analysis and HLD | Detailed Design | Build & System Test | Acceptance Test | Performance Test | Market Trials | Regression Test | Imp. | PIS
Track 1 Baseline Plan | 10/01/18 | 07/02/18 | 11/04/18 | 13/04/18 | 13/04/18 | 04/06/18 | 13/08/18 | 07/09/18 | 19/10/18 | 08/10/18* | 22/10/18 | 02/11/18 | 04/01/18
Track 1 Current Plan | 10/01/8 | 07/02/18 | 11/04/18 | 13/12/17 | 13/04/18 | 04/06/18* | 13/08/18 | 07/09/18 | 25/10/18 | 08/10/18* | 22/10/18 | 02/11/18 | 04/01/18
Track 2 Baseline Plan | 10/01/18 | 07/02/18 | 11/04/18 | 13/04/18 | 13/04/18 | 30/06/18* | 24/09/18 | 05/11/18 | N/A | 14/12/18* | 18/01/18 | 01/02/19 | 08/03/19
Track 2 Current Plan | 10/01/8 | 07/02/18 | 11/04/18 | 13/12/17 | 13/04/18 | 30/06/18* | Build Complete ST synergised with AT | 14/12/18** | N/A | 14/12/18* | 18/01/18 | 04/02/19 | 08/03/19
RAG Key – Milestones are end dates;
*Closedown expected to finish this week ** Synergised ST and AT date
Milestone date forecast to be missed
Milestone date forecast to be at risk
Milestone date forecast to be met
Milestone completed
Planning/Milestone date to be confirmed

## Slide 20: 5b. XRN4802 – MiR Drop 3 - Status Update
01/04/19 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | PIS – All activities completed Closedown – Project completed PIS with Handover to Xoserve Operate accepted |  |  | 
Risks and Issues | All RAID items for Drop 3 closed down following project completion and handover |  |  | 
Cost | All costs tracked to budget |  |  | 
Resources | No resource requirements for Drop 3 as the project has now closed down and handover is complete |  |  | 

## Slide 21: XRN4802 – MiR Drop 3
Minor Release Key Milestone Dates:
22nd March – PIS completed and Handover to Xoserve Operate accepted – Project now closed
2019
May
Jun
Jul
Aug
Sept
Oct
Nov
Dec
Jan
Feb
Mar
2018
Testing
Build
UT
Imp
Apr
Feb-19 Minor Release Timeline
Design
Build
ST & Assurance
CM
PT / RT
IMP
PIS
Feb-19 Minor Release Timeline

## Slide 22: 5c. XRN4732 - June 19 Release - Status Update
18th March 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | System Testing : Testing has commenced and is continuing to plan to be completed by 29th April Plan: Tracking to plan, detailed testing phases have been planned out, implementation planning and assessment has started alongside System Testing Funding: The BER was approved by ChMC at the 09th January 19 meeting |  |  | 
Risks and Issues | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, AML/ASP etc) and all requirements are able to be met Environments– There is a risk that multiple projects are running in parallel (EUC, June 19 & GB Charging) a detailed assessment of plans and co-existence in pre-production is in progress |  |  | 
Cost | Project delivery costs are tracking to approved budgets |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 23: XRN4732 - June 19 Release Timelines
Key Milestone Dates:
Build and UT has completed
ST+SIT has now commenced

## Slide 24: 5d. XRN4665 – EUC Release
01/04/19 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Build & UT : Build & UT activities on track to complete as per planned milestone date Testing : ST & SIT activities commenced as per plan and currently running to schedule Implementation : Change Pack distributed for information on 15/03 to inform industry colleagues of the following implementation dates; Part A on 03/08 to make new EUC bands allowable in ISU to enable sharing of new EUC bands with Industry via the T67 file Part B on 31/08 (with a contingency date of 07/09 if required) to implement all code changes to processes affected by new EUC bands |  |  | 
Risks and Issues | Environments– There continues to be a risk that multiple projects are running in parallel (EUC, June 19 & GB Charging). A detailed assessment of co-existence in Pre-production is currently in progress with relevant project teams. However the current view is that this should not impact the EUC release. |  |  | 
Cost | Project delivery costs are tracking to approved budgets |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 25: XRN 4665 - EUC Release Timelines
Key Milestone Dates:
Build & UT activities tracking to plan for completion by planned milestone date
ST/SIT activities commenced as per plan and currently tracking to schedule
Internal discussions ongoing to agree PIS duration (to include first usage monitoring)

## Slide 26: XRN4828 - Nov 19 Release - Status Update
1st April 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Start Up and Initiation phase in progress and on track to complete in April Planning for Design phase being finalised with selected vendor. Slightly behind planned date of 1st April, due 5th April. Market Trials phase discussed at ChMC and agreement reached in principle that this is not required for November 19 release. Alternative options to MT to be discussed on 1st April DSG. Change Packs on track to be approved by 8th May Funding: BER for full delivery to be presented to ChMC in April 2019 |  |  | 
Risks and Issues | Risk: There is a risk that the Nov 19 Release may be impacted by Pre-Production environment congestion due to multiple deliveries running in parallel Risk: There is a risk that due to multiple UKLink deliveries running in parallel there may be limited access to resources. |  |  | 
Cost | The BER with full delivery costs will be presented to ChMC in April 2019. |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 27: XRN4828 - Nov 19 Release Timelines
Key Milestone Dates:
Receive supplier responses – 13/02/19
Supplier contract approval – 05/04/19
Approve and issue EQR – 04/02/19
Gain Business Case approval at IRC - 13/03/19
PID approval 12/04/19
Detailed Delivery Plan approved – 05/04/19
BER Approval – 10/04/19
Design Change Packs Submitted to Industry –08/05/19
Test Plan approval – 05/04/19
2020
Feb
Mar
Apr
May
Jun
Jul
Aug
Sept
Oct
Nov
Dec
2019
J
u
n
e
1
9
–
C
h
M
C
A
g
r
e
e
d
S
c
o
p
e
Testing
Build
UT
Imp
Mobilisation
Jan
Design
Build & UT
System Test
SIT
UAT
RT & PT
Market Trials
IMP (Inc IDR)
PIS
Closedown
04/02: EQR Approval
10/04: BER Approval
08/05: Change Pack Submission
Nov-19 Timeline

## Slide 28: Assurance In Place of Market Trials
Option 1 – Do Nothing
  Xoserve would not look to provide any alternative to provide assurance in place of Marker Trials
  Confirmation of successful Acceptance, Performance & Regression Testing would be confirmed
Option 2 – Provide Test Summary Report
  Xoserve will produce a summary report at the completion of testing and ahead of Implementation providing details of successful test completion including Test Case pass rate and defect figures

## Slide 29: 6. New Change Proposals For Ratification of the Prioritisation Scores
No agenda items for this section

## Slide 30: 7. Change Proposal Initial View Representations
7a. XRN - XRN4871 - Modification 0665 – Changes to Ratchet Regime
7b. XRN4645 – The Rejection of Incrementing Reads Submitted for an Isolated Supply Meter Point (RGMA Flows)
7c. XRN4780 - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
7d. XRN4789 - Updating Shipper Reporting Packs and glossary

## Slide 31: 7a. XRN4871 - Modification 0665 – Changes to Ratchet Regime

## Slide 32: Background
Modification 0665 has been raised and seeks to amend the current Class 2 Ratchet Charging Arrangement and it allows Transporters to designate Supply Points (Network Designated) that should, in addition to existing mandatory Class 1 Supply Points, be subject to the existing Class 1 Ratchet Charging Arrangement.
This Change Proposal has been raised to deliver the system requirements set out within this modification.
Due to the proposed timescales and the requirement to implement the changes by 01 October 2019, the Change Proposal has been raised ahead of the modification being officially approved (Panel approval expected March and Ofgem decision April).
Implementation is being proposed as the July Minor Release.

## Slide 33: Last DSG Meeting – 18 March 2019
During the last meeting, we requested views from DSG on certain solution options / assumption (options/assumptions are detailed within the following slides).
DSG acknowledged that the options presented were pragmatic and agreed for an extraordinary Change Pack to be issued to solicit wider industry views.
An extraordinary Change Pack was issued on 19th March closing on 27th March. Five parties responded, three of which supported our approach and two made general comments/observations but did not raise any major concerns.
Slides 4-7 recaps the options / proposed approach and includes reference to the industry representation we received.

## Slide 34: Visibility of ND Flag
As part of application of Network Designation the Registered User will receive a notification to the DSC Contract Manager from the CDSP
Visibility of Network Designation to Prospective Users
  As we are seeking to limit the scale of impacts to Users, and in particular Users who do not operate DM Supply Points, we are NOT proposing to make this data item available to Shipper Users in SPA files – e.g. Nomination Response (including Enquiry); Confirmation; etc.
  We would suggest that if there is a requirement to make this data item available in SPA files, that this is considered within the CSS Consequential interface changes – scheduled for 2021
  If the industry believes that Prospective Users need to have visibility of the Network Designation, potential options could be:
    Changes to DES
      This is not recommended as the change may be precluded by the timescales.
    Addition to API services
      This would be the preferred option if visibility was required but would need to be assessed.
Industry representation indicated that Users were comfortable with the approach to not amend file formats for this implementation and were comfortable with this being considered as part of CSS changes especially if the number of these sites were to grow significantly over time.

## Slide 35: Views sought from DSG - SPA
Rejection of Nomination / Confirmation (including Reconfirmation) / Class Change
  If a site is Network Designated it must be Class 1, any relevant transactions will need to be rejected, such as:
    Nomination
    Confirmation
    Class Change
  We would propose that we use the existing Rejection Code CLS00002 – “Supply meter point should be Class 1”. This code is used for the above processes already.
  Shippers need to consider if this rejection will cause exceptions within their systems as the site will not meet the current Class 1 requirements.
From the industry representation, Users did not flag concerns with this approach. It was suggested by one User that a new rejection code would be sensible. This will need to be considered as part of design but the majority were happy with the utilising the rejection code suggested and did not believe it would cause exceptions in User systems that could not be managed.

## Slide 36: Views sought from DSG – Inflight
Outstanding Offers and Inflight Change of Shipper / Capacity Revision
  The industry needs to consider where a Supply Meter Point gets set to Network Designated but has and outstanding offer or an accepted confirmation:
  Outstanding Offer on a Network Designated site which has a Class other than Class 1
  We could:
  Invalidate Offer
  Reject the Confirmation where the Shipper attempts to confirm an Offer on a Network Designated Supply Meter Point
  Allow Offer to continue, but oblige Shipper to reclassify the SMP
  Accepted Confirmation on a Network Designated site which has a Class other than Class 1
  We propose to allow Confirmation to progress, but oblige Shipper to reclassify the SMP
From the industry representation, Users agreed with our approach to allow the Confirmation to progress.

## Slide 37: Views sought from DSG – Invoicing
New Ratchet Charging Arrangement
  The current Ratchet Charge includes the ZRA – Customer Ratchet Charge and the SRA – SOQ Ratchet Charge
  The new Ratchet Charge for Class 2 sites will also include the ECN – Exit Capacity LDZ Charge. This is planned to be incorporated into the ZRA Charge for Class 2 Ratchets only
    This appears on the CAZ Invoice and ZCS Supporting information
    The RT_I09_CAP_RATCHET_CHARGE_DETAIL record has the RATCHET_PREMIUM value which we expect will be populated differently between Class 1 and Class 2 Ratchets. This needs to be considered by Shippers.
From the industry representation, Users were not concerned with the proposed changes. It was stated by one User that changes to the file structure (which is not proposed) would cause an issue and a value/rate change is manageable (which is being proposed).

## Slide 38: Next Steps…
We appreciate the feedback from DSG / through the industry representation and note that the general consensus is that Users are comfortable with the options proposed and suggested implementation (July Minor Release) providing there is no change to actual structures.
Please note that the options/approach presented to date are a first draft only and this will all need to go through a thorough assessment.
We will consider the representation we have received and take the change through detailed design which is currently unconfirmed.
The outcome of the detailed design will be shared with DSG and the wider industry through the usual change process.

## Slide 39: 7b. XRN4645 – The Rejection of Incrementing Reads Submitted for an Isolated Supply Meter Point (RGMA Flows)
Slides to be provided by 01/04/19

## Slide 40: 7c. XRN4780 - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)

## Slide 41: Overview
XRN4780 has been raised to look at adding in MAP Identifier into UK Link
This change is a result of a requirement to pass the MAP Id to CSS so they can be informed as part of a switching event
July-19 scope includes acceptance/storing of Market Participant (ASSPR - Asset Provider) contained in submitted RGMA files within UK Link

## Slide 42: RGMA Logic Overview
Where an accepted RGMA (JOB) contains a valid MAP Id
  Current MAP Id is end dated and new MAP Id is populated
Where an accepted RGMA (JOB) does not contain a valid MAP Id or MAP Id is not provided
  Current MAP Id is removed/end dated
Where an accepted RGMA (UPD) contains a valid MAP Id
  Current MAP Id is end dated and new MAP Id is populated
Where an accepted RGMA (UPD) does not contain a valid MAP Id or MAP Id is not provided
  Current MAP Id is retained

## Slide 43: RGMA Logic Overview cont.
Previous slides reference ‘valid’ MAP Id
RGMA Files (JOB/UPD) contains MKPRT record containing the following…
  A0177 | Record Identifier | MKPRT
  A0126 | Role Code | ASSPR
  A0064 | Market Participant Abbreviated Name | ###
A0064 has a length of 12 (as this record is also used for Meter Worker [MTWK] information)
MAP Id has a standard 3 character length
Validation will be carried out on inbound RGMA’s and only MAP Id’s that are referenced in our organisation table will be classed as valid and loaded

## Slide 44: 7d. Reporting XRN delivery recommendations
Seek agreement from DSG on how to progress reporting changes

## Slide 45
There are currently a number of Reporting Changes being progressed through capture in the Customer Change Lifecycle Team.
These changes will predominately require resource from the same teams and the same tables within SAP BW. They will also need similar changes and testing to be carried out to deliver the changes.
The purpose of this document is to seek agreement from DSG on how to progress these changes in order to do the following:
  Limit the amount of regret spend
  Deliver the changes to Shippers in the optimum timeframe
  Provide benefit to shippers by giving meaningful usable management information
  Provide a medium term solution to reporting requirements until such times as the Reporting Review is complete.
The following options and recommendations have been made by Xoserve and we are seeking feedback on the recommendation from DSG Members to then be able to present the recommendation to Change Management Committee for ratification.
Shipper Pack, PARR Reporting XRN delivery recommendation

## Slide 46: Shipper Pack, PARR Reporting XRN delivery recommendation
Description:
XRN4789 has been raised to address the format of the Shipper Reporting Pack. It will look to add value by changing the glossary to make it more user friendly and also align the data reported post Nexus to product class from AQ band. It also looks to change the lay out to make the data easier to interpret by Shippers
Problem Statement & Objective:
There are a number of outstanding change requests in progress which overlap in terms of data source and reporting purpose. The objective of this recommendation is to agree the best way to approach these XRN’s to minimise regret spend and provide value and benefit to customers as soon as possible.
Benefits / Financial Impact:
Indicative costs to change in isolation - £20k
Option 1 – Progress the Shipper Pack report changes only (XRN4789): Indicative costs – £20k
Pros: Cons:
Changes will be progressed as planned and change can be assigned to delivery team as early as 3rd April.
Shipper Packs will be structured better so that the data can be divided up by departments to work.
Aligns the Shipper Packs to the changes made as part of Nexus – reporting by Product Class rather than AQ.
Shippers will be provided with some of the supporting data to review when challenged by PAC.
Risk: Regret spend may be incurred by shippers – due to the number of similar reporting changes code may be changed for this and then again changed soon after.
Risk: Making these changes in isolation might lead to delays in delivering the PARR Reports due to availability of resource and testing environments.

## Slide 47: Shipper Pack, PARR Reporting XRN delivery recommendation
Description:
XRN4864, XRN4779 and XRN4876 have been raised to provide additional data items for PAFA and the PARR Reports. This data can then assist shippers in monitoring their own performance and addressing any issues prior to them being notified by PAC.
Problem Statement & Objective:
There are a number of outstanding change requests in progress which overlap in terms of data source and reporting purpose. The objective of this recommendation is to agree the best way to approach these XRN’s to minimise regret spend and provide value and benefit to customers as soon as possible.
Benefits / Financial Impact:
Reduce regret spend.
Indicative costs to change in isolation – unknown currently pending outcome of this recommendation (to avoid regret spend).
Option 2 – Progress the PARR report changes ( XRN4864, XRN4779 and XRN4876) only: Indicative costs – not currently known
Pros: Cons:
Progressing these changes together will provide the majority of lower level data needed by Shippers to take corrective action should they be notified by PAC of poor performance.
Some of the additional data being delivered will also fulfil some of the UIG Taskforce recommendations and committee approved routes for delivery therefore is a strategic initiative.
Avoids making changes to the Shipper Packs which may become obsolete once the PARR Reports have more supporting information therefore minimising regret spend.
Risk : May still need to make the changes to the shipper packs should it be discovered in detailed design that the best place to display the data is in the Shipper Packs – currently reporting at AQ and not Product class.
Risk: May require additional investment for providing the data at lower level granularity due to size and transfer of data – possible will need SFTP route or secure location in the cloud to host.

## Slide 48: Shipper Pack, PARR Reporting XRN delivery recommendation
Description:
Within XRN4789 there is a request to update the glossary to make it more relevant.
As per Option two there are four PARR Reporting changes which will have similar code changes and require the same resource to develop and test.
Problem Statement & Objective:
There are a number of outstanding change requests in progress which overlap in terms of data source and reporting purpose. The objective of this recommendation is to agree the best way to approach these XRN’s to minimise regret spend and provide value and benefit to customers as soon as possible.
Benefits / Financial Impact:
Reduce regret spend.
Indicative costs to change in isolation – unknown currently pending outcome of this recommendation (to avoid regret spend).
Option 3 – Progress the glossary changes for the Shipper Packs and deliver all the PARR Report XRNs together - not currently known
Pros: Cons:
Progressing the Shipper Pack Glossary changes will provide immediate benefit to all Shippers including new entrants to the market
Progressing these changes together will provide the majority of lower level data needed by Shippers to take corrective action should they be notified by PAC of poor performance.
Some of the additional data being delivered will also fulfil some of the UIG Taskforce recommendations and committee approved routes for delivery therefore is a strategic initiative.
Avoids making changes to the Shipper Packs which may become obsolete once the PARR Reports have more supporting information therefore minimising regret spend.
Risk: May still need to make the changes to the shipper packs should it be discovered in detailed design that the best place to display the data is in the Shipper Packs – currently reporting at AQ band and not Product class.
Risk: May require additional investment for providing the data at lower level granularity due to size and transfer of data via the Shipper Pack – possible will need SFTP route or secure location in the cloud to host.

## Slide 49
1- BO Generated Reports
Existing reports will be amended and 2 new reports created to recreate the current charts that are manually created as of today Two new reports created on existing data model in BO Defect fix is required as none of the required reports will be possible without it The BW table DA_FCST_ALLOC_LDZ_UIG that is sourced from Gemini, and the ISU sourced table CONH will be used to populate all 3 charts: Weekly UIG Stats Allocation Reconciled UIG Post Rec
Recommended Option 3: Progress the glossary changes for the Shipper Packs and deliver all the PARR Report XRNs together
Option 3 is recommended for the following reasons:
It delivers on all changes, albeit partially for XRN4789 but the glossary changes add immediate value.
Minimises the level of regret spend – if tables in the system are being modified at the same time for all changes. development and testing can be done once rather than several times.
Delivers a strategic approach to change for customers.
Adds value for UIG by giving access to the data that impacts shippers and UIG.
Provides a mid term approach to reporting until delivery of XRN4857 (Reporting Review) and the rationalisation of all reports.
Shipper Pack, PARR Reporting XRN delivery recommendation
Shipper Pack Glossary changes
PARR Report Changes
UIG Reports
Shipper Pack Changes
Q2 ‘19
Q3 ’19 (indicative)

## Slide 50: 8. Undergoing Solution Options Impact Assessment Review
8a. XRN4833 - Roll Out of Business Intelligence and Data Discovery Capability
Verbal update to be presented by Jason McLeod

## Slide 51: 9. Solution Options Impact Assessment Review Completed
9a. XRN4713 - Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690)
9b. XRN4803 - Removal of validation for AQ Correction Reason 4

## Slide 52: 9a. XRN4713 - Actual Read following Estimated Transfer Read Calculating AQ of 1 - Enduring Solution
High Level Solution Option Assessment

## Slide 53: Change Overview
XRN4713 - Actual Read following Estimated Transfer Read Calculating AQ of 1 - Enduring Solution
The original change proposal XRN4690 was raised, and following solution review the recommendation was to implement a transitional/temporary solution (‘Option 2’) to carry forward the prevailing Rolling AQ in the instance of a negative consumption value being in the first variance period considered for the AQ process. XRN4713 was raised to look at options for an enduring solution that would consider the possibility of re-estimating the Shipper Transfer Reads following receipt a cyclic read that causes a negative consumption. As agreed at DSG & ChMC solution option 3 (reporting out to Shippers) was agreed to move forward into a HLIA
Solution Options
Do nothing
Re-estimate transfer read
Notification (report to Shippers)
1
2
3

## Slide 54: Option 3 - High Level Impact Assessment
3 - Notification (report to Shippers)
Report to be created informing inbound and outbound Shippers of the presence of a negative consumption pre or post either Shipper Transfer, Class Changes & Re-Confirmations.
Impacted Systems
Assumptions
Shippers to be only recipient All Class’s to be considered
Overall Impact | Release Type | High Level Cost Estimate
Low | Data Release | 0 – 15,000 GBP
Marketflow
SAP PO
SAP ISU
Gemini
SAP BW
CMS
DES
API
Impact
3

## Slide 55: Option 3 - System Impact Assessment
System Component:
Development Type:
Impacted User(s):
Build Type:
Change Description:
Requirement Clarity:
Change Complexity:
Integration Complexity:
Test Data Prep Complexity:
Test Execution:
Regression Testing Impact:
Performance Impact:
SAP BW |  |  |  |  | 
Report Production |  |  |  |  | 
Creation |  |  |  |  | 
Shippers |  |  |  |  | 
New |  |  |  |  | 
Report highlighting presence of a negative consumption pre & post either Shipper Transfer, Class Changes & Re-Confirmations |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
3
Notes: System Component: File Format / Batch Job / Process Code / Report
Development Type: Interface / Online / Report / Workflow / Configuration
End User Impacted: Shipper / DN / NTS / Xoserve / Other
Build Type: New / Existing

## Slide 56: Option 3 - Process Impact Assessment
Process Area | Complexity | File Formats | Exceptions | External Screens | Batch Jobs | Performance Test?
SPA | n/a | n/a | n/a | n/a | n/a | n/a
Metering (Reads) | n/a | n/a | n/a | n/a | n/a | n/a
Reconciliation | n/a | n/a | n/a | n/a | n/a | n/a
Invoicing – Capacity | n/a | n/a | n/a | n/a | n/a | n/a
Invoicing – Commodity | n/a | n/a | n/a | n/a | n/a | n/a
Invoicing – Amendment | n/a | n/a | n/a | n/a | n/a | n/a
Invoicing – Other | n/a | n/a | n/a | n/a | n/a | n/a
Rolling AQ | n/a | n/a | n/a | n/a | n/a | n/a
Formula Year AQ | n/a | n/a | n/a | n/a | n/a | n/a
RGMA | n/a | n/a | n/a | n/a | n/a | n/a
DSC Service | n/a | n/a | n/a | n/a | n/a | n/a
Other (Specify) | L | N | N | N | N | N
3

## Slide 57: 9b. XRN4803– Removal of validation for AQ Correction Reason 4
High Level System Solution Impact Assessment

## Slide 58: Change Overview
XRN 4803 – Removal of validation for AQ Correction Reason 4
There have been instances where a users read is being rejected as it breaks the outer tolerance, and AQ correction is being rejected as the AQ has not been re-calculated in the UK Link system. Therefore there is no option to correct the incorrect AQ; hence the user can’t submit reads. Therefore we will never be able to reconcile or get a correct AQ calculated.
Solution Options
Remove the ‘calculated’ validation check when a site is/was unregistered or shipperless prior to current registration
1

## Slide 59: Option 1 - High Level Impact Assessment
1- Remove the ‘calculated’ validation check when a site is/was unregistered or shipperless prior to current registration
Currently if AQI is received with reason code 4 and AQ Roll has been recalculated; then only AQI will be accepted if all other validations are successful. After this change the above mentioned validation will be removed. Irrespective of the AQ Roll calculation has taken place or not; AQI will be accepted if all other validations are successful.
Impacted Systems
Assumptions
Market Trials costs are not considered. This change is applicable only for Reason Code 4 in AQI. Reason code 1,2,3 and 5 are out of scope of this change. All the other AQI validations will continue As Is.
Overall Impact | Release Type | High Level Cost Estimate
Low | Minor | 15,000 - 25,000 GBP
Marketflow
SAP PO
SAP ISU
Gemini
SAP BW
CMS
DES
API
Impact
1

## Slide 60: Option 1 - System Impact Assessment
System Component:
Development Type:
Impacted User(s):
Build Type:
Change Description:
Requirement Clarity:
Change Complexity:
Integration Complexity:
Test Data Prep Complexity:
Test Execution:
Regression Testing Impact:
Performance Impact:
SAP ISU |  |  |  |  | 
Process Code |  |  |  |  | 
Code Change |  |  |  |  | 
Shippers |  |  |  |  | 
Existing |  |  |  |  | 
System will be amended to remove the “previously calculated” validation on AQ Correction process for reason code 4 |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
1
Notes: System Component: File Format / Batch Job / Process Code / Report
Development Type: Interface / Online / Report / Workflow / Configuration
End User Impacted: Shipper / DN / NTS / Xoserve / Other
Build Type: New / Existing

## Slide 61: Option 1 - Process Impact Assessment
Process Area | Complexity | File Formats | Exceptions | External Screens | Batch Jobs | Performance Test?
SPA | L | N | N | N | N | N
Metering (Reads) | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Reconciliation | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Invoicing – Capacity | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Invoicing – Commodity | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Invoicing – Amendment | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Invoicing – Other | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Rolling AQ | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Formula Year AQ | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
RGMA | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
DSC Service | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Other (Specify) | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
1

## Slide 62: 10. Miscellaneous
10a. XRN4777 – Acceptance of contact details updates

## Slide 63: 10a. XRN4777 – Acceptance of Contact details updates
Coming to the end of detailed design phase, issue identified with design
  Current design:-
    When validating CNC and EMR files the process will check when file is received and validate the effective date against received date, so any files received on the day after daily process will still be accepted when processed the next day (providing effective date does not pre-date file receipt date)

## Slide 64: XRN4777 – Acceptance of Contact details updates
Potential issue:
    Sequencing has not been considered for this change
    Files do not necessarily process in the order they are received
    Risk if multiple updates are sent the latest update may not be processed last

## Slide 65: XRN4777 – Acceptance of Contact details updates
Options:
    1. continue with design as is
      Clearly communicate design as some processing issued cause problems (no need to end date prior to updating new contact details)
    1a. Continue with design implement sequencing later
    2. Add sequencing into the design
      Unable to deliver in July 2019 minor release
      Significantly increase cost

## Slide 66: 11. JMDG Update

## Slide 67: 27 Domestic M-Number Helpline [Gas]
Solution overview
Use case overview
Replace the existing method of providing this service with an online solution
500k calls per year, used by domestic consumers
JMDG progression
Assessed, prioritised and requested project team to provide solution.
Phase 1 – Web Portal has been delivered to gas consumers. Consumers can obtain MPRN, Gas Supplier and Transporter name
Phase 2 –Enhancement to Web Portal. Key updates include fuzzy matching on searches, more searchable fields and inclusion unregistered sites.
Plan
Phase 1 was delivered in September 2018. Phase 2 has commenced and is on track to launch in June 2019
Testing
Phase 1
Phase 2
Requirements
Gathering
27

## Slide 68: 06 MAPs - Meter Asset Details [Gas]
Solution overview
Use case overview
Meter asset data on UK Link is not correctly maintained by industry participants
A reporting service will be provided to compare the MAM / MAP meter point reference number and meter serial number to that held on UK Link
JMDG progression
Assessed, prioritised, requested project team to analyse requirements with MAPs
06
Engage Maps
Portfolio
Analysis
Phase 1 – MAPs to UKLink meter asset comparison service (Dec ’18) - Completed
Phase 2 – MAP to MAP meter asset comparison service (May ‘19) – In Progress
Phase 3 – Introduction of MAP ID into UKLink (CSSC) – Enduring solution (TBC – would be linked to a UKLink Release schedule)
MAP
Engagement
Process
Modelling
Service
Set-up
JMDG
Phase 1
Phase 2
Design /
Procurement
Development

## Slide 69: 33 Third Party Services [Twin]
Overview
Use case overview
Provide data services to Third Parties
JMDG progression
Assessed, prioritised, requested project team to conduct initial analysis
23
Permissions
Workshop
Raise MOD 649
A gas data permissions matrix has been created detailing current industry participants permissions to data
The data permissions matrix will help highlight potential API services. MOD 649 will help expedite the governance process to provision data new data services to industry participants while still providing a robust approval process
MRASCo Board has been establishing precedents for third party access approach, which can supplement the gas matrix
A Third Party industry engagement approach was been created
workshop
Engagement Plan
Start Engagement
MOD 649 Approval
JMDG

## Slide 70: 47 & 09 ASC and CT / VT Ratio (Electricity)
Solution overview
Use case overview
Two linked cases involving DNO data:
047: The MIS could also facilitate access to Current/Voltage Transformer (CT/VT) ratio. The ratios would be populated initially by the distribution network operator and can be queried by Parties should discrepancies be identified as part of meter installation, or commissioning and proving tests.
009: Proposed making EAC available to quoting suppliers, and mentioned inclusion of ASC
Initial discussions suggest data will be available but DNOs not keen on multiple access to their databases.
Possibility of ASC access via aggregator model with one authorised API gaining access. This also means less development time.
Timescales: Specification work 3 months. Solution development (subject to BSC for CT/VT) 3 months. Testing I month. Go live May to August 2019.
JMDG progression
Indicative costs received from ECOES service provider. JMDG decided to progress to full solution design. MIS project team prioritised EAC use case for February meeting. Will refocus on this for March’s meeting.
47
Progress to Full Solution

## Slide 71: 01 & 57 Central industry contact database and Industry Escalation Process
Overview
Use case overview
Central repository for industry contact details to underpin industry processes
JMDG progression
Assessed, prioritised, requested project team to conduct initial analysis
09
Both cases can use the same information contained within current code processes. Initial discussions suggest data available but code administrators generally not willing to co-operate so may need changes to code to enforce compliance.
Timescales: Specification 3 months. Possible modification processes 3-9 months. Solution development 3 months. Testing I month. Go live may be incremental Feb 2019 to November 2019.
JMDG and MPB
decision making
Governance changes
and development

## Slide 72: 09 Estimated Annual Consumption (EAC)
Overview
Use case overview
Make EAC available to quoting supplier
JMDG progression
Indicative costs received from ECOES service provider. JMDG to decide on progression to full solution design based on outcomes of EAC workshop held 28/01/2019 – report provided to JMDG in enclosures for February meeting.
09
Workshop held 28th January to explore potential sources, formats, frequency of the data
Options assessment being presented to February 2019 JMDG
Followed by impact assessment of preferred option and JMDG progress/don’t progress decision
JMDG options
assessment
Second order analysis and
impact assessment
JMDG and MPB
decision making
Implementation
Options assessment
workshop

## Slide 73: 56 FiT Licensee Notifications – Smart meter installs
Use case overview
FiT Licensees would be better able to meet their Supply Licence obligation to administer export payments on metered data whenever possible if a mechanism existed to inform them that a smart meter (which by definition has export metering capability) has been installed on the premises of a FiT Generator
JMDG progression
JMDG agreed high priority progression. Ofgem attending December meeting to participate in discussion on solutions. Gemserv are impact assessing options for delivering the requirements JMDG wanted to progress with their service providers. We will report back in March.
56
ECOES contains meter information (meter serial number, meter type) which would allow FiT Licensees to identify if import MPAN associated with a FiT Generator had a smart meter installed
Either make relevant ECOES data through the Central FiT Registry or combine the two data sets and make available to FiT Licensees elsewhere
Another example of “Trusted Third Party API” requirement which could be handled in aggregate.
An example of where ‘push’ functionality on the API might be of benefit.
JMDG and MPB
Assessment and decision
Options Overview

## Slide 74: 58 MAP API [Gas]
Overview
Use case overview
There is an opportunity to create a service where MAPs can query the current and historic Supplier ID for assets installed on a supply meter point
JMDG progression
Assessed, prioritised, requested project team to move to delivery
58
Change Proposal has been raised and sponsored by Colin Blair (MPB Member)
Project team to provide ChMC feedback to MAPs post meeting to highlight any considerations
Dependency: Change is dependant on MOD and Data Permission Matrix (DPM) Amendment approval
ChMC
Review
Submit MOD
CoMC DPM
Amendment

## Slide 75: 59 UKRPA Access to Gas data [Gas]
Overview
Use case overview
There is an opportunity to create a service where MAPs can query the current and historic Supplier ID for assets installed on a meter point
JMDG progression
Assessed, prioritised, requested project team to move to delivery
59
To ensure consistency with other related parties who have also requested access to gas data for theft investigation, Xoserve are exploring the strategic approach for this type of request
ChMC
Review
Submit MOD
CoMC DPM
Amendment

## Slide 77: 12. Action Updates
The DSG Actions Log to be published on the DSG pages of Xoserve.com

## Slide 78: 13. AOB
13a. Website Update – Change Packs and Change Proposals.

## Slide 79: Website Update – Change Packs
DSG on 1st April 2019

## Slide 80: Background
Currently, we manage the Change Pack process via email
  We send big emails to our customers, which include individual attachments
  We manually collect responses, and we send Representation Matrixes to our customers via email
The current process requires improvement
  Email consultations are not user friendly for our customers
  As we manually collect responses, we sometime miss them
  There is no central reference point for referring to Change Packs
We are working to implement a ‘digitalised’ solution whereby we manage the process via Xoserve.com, replacing the existing email mechanism
  Customers will be able to review Change Packs, and submit responses, via the website
  There will be a dedicated page on the website for Customers to refer to Live and Closed Change Packs
  There will some degree of automated ‘rep collection’
The next slides shows how it will work

## Slide 81: How will it work?
Customers receive a tokenised url from Xoserve
Consultation Period
Customers can read, download and send, and provide reps on the website
D = When Customers receive the Change Pack
D+10
D
The website will automatically collate customer reps; public reps can be published on the website within 24 hours of submission
Xoserve publish the Representation Matrix on the website
D+15
Some key points for customers:
‘Private’ reps will be sent automatically via email to the UK Link Manual box account, and won’t be published on the website
For late reps, customers will have to download the Change Pack document, fill in the appropriate response section, and send it to the UK Link Manual box account; the system doesn’t recognise late reps
It is technically possible for an organisation to submit multiple reps; we only expect one rep per organisation as per existing process

## Slide 82: Initial Design
The following links to our initial design of the Change Pack Mechanism:
https://xd.adobe.com/view/c714ed62-c06a-4baa-74e7-daba4cc2ff74-b125/?fullscreen
We are expecting implementation in preparation for the May Change Pack
We have an external Pilot Group to test the solution on 29th April, and we have a couple of other external demonstration events planned before implementation: if you would like to register your interest, please write to Richard at uklink@xoserve.com
Is there any questions before I talk about another initiative for the website?

## Slide 83: Change Proposal Form on Xoserve.com
Currently, if you want to send a Change Proposal to Xoserve.com, you have to download a template from the Joint Office, fill it in and then send it via email to the Xoserve Portfolio Office
Soon, you’ll be able to submit an online CP form via Xoserve.com. Once you’ve completed the form, your online form will transfer into a Change Proposal word document, and it’ll be sent directly to the Portfolio Office automatically
Here is our initial design:
  https://xd.adobe.com/view/b2ed28cc-f77c-4f4f-5961-12d7a47f8846-c4dc/