## Slide 1: DSC Delivery Sub-Group
May 2026

## Slide 2
1b
1.1 Lorem ipsum
Action Updates
REC Change
NESO – Verbal Update
Previous DSG Meeting Minutes
1. General Meeting Administration

## Slide 3: 1b
The DSG Actions Log will be published on the DSG pages of Xoserve.com

## Slide 4
SECTION 2:
Change Development
02
2a. New Change Proposals
2b. Undergoing Solution Options Impact Assessment Review

## Slide 5
SECTION 2:
Change Development
2a. New Change Proposals
2a.i XRN 6079 UNC 0926S Maintenance criteria for Emergency Contact data held in Central Systems
2a.ii XRN 6081 Meter Read Service Improvements
2a.iii XRN 6081.A - Fix Historic NDM Check to Check Reconciliation Periods - Tactical Solution
2a.iv XRN 6081.B - Reconciliation of Multiple Read Replacements – Historic Reporting and Tactical Solution
2a.v XRN 6081.C - NDM Check to Check Reconciliation – Enduring Solution
2b. Undergoing Solution Options Impact Assessment Review
2b.i XRN XRN 5994 - Emergency Contact Validation Service

## Slide 6: XRN 6079 UNC 0926S Maintenance criteria for Emergency Contact data held in Central Systems
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | X
This vote is to approve the change into development | 
Change Type | Regulatory
Priority | High
Proposer | Cadent
Change Proposal | Link to CP
Change Description
This Change Proposal has been raised to deliver the Central System changes required as set out within UNC 0926S. This modification outlines the criteria for how all emergency contact data (EMR data) must be recorded and maintained in Central Systems.
DSC Service Area Associated Funding Split | Service Area 3 - Manage updates to customer portfolio
Proposed Funding split from Proposer | Shipper 90% DNO 10%

## Slide 7: XRN 6081 Meter Read Service Improvements
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | 
This vote is to approve the change into development | 
Change Type | Non - Regulatory
Priority | Medium
Proposer | Xoserve
Change Proposal | Link to CP
Change Description | 
This Change Proposal will act as a parent to group the individual Change Proposals and as a central point of reference for customers. Subsequent Change Proposals will be raised to address issues identified in the meter read and reconciliation processes. These are: | 
A Fix Historic NDM Check to Check Reconciliation Periods - Tactical Solution B Reconciliation of Multiple Read Replacements – Historic Reporting and Tactical Solution C NDM Check to Check Reconciliation – Enduring Solution D Reconciliation of Multiple Read Replacements – Enduring Solution E Read Inserted Prior Expected Class 4 Opening Read - Volume and Energy Calculation | F Read Validation where no Actual Read Present in Previous Class Period G Reconciliation of Class Change with subsequent Shipper Transfer and Class Change H RGMA Read Validation where Site Flagged as AMR I NDM Opening Read Estimation Based on Read with a Positive Through The Zero Count J Twin Stream Volume Aggregation
DSC Service Area Associated Funding Split | Service Area 4 : Meter Read/Asset processing
Proposed Funding split from Proposer | Shipper 33% DNO 67%

## Slide 8: XRN 6081.A - Fix Historic NDM Check to Check Reconciliation Periods - Tactical Solution
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | 
This vote is to approve the change into development | 
Change Type | Non - Regulatory
Priority | Medium
Proposer | Xoserve
Change Proposal | Link to CP
Change Description
The objectives of this Change Proposal are to: 1. Review and analyse all C2C periods, currently available for adjustment, to establish the impact of the defined problem 2. Correct the position of the incorrect reconciliations, identified in step 1, through an automated process to apply consumption adjustments 3. Utilise the automated process as a, proactive, tactical solution ahead of the full solution being developed under part C, NDM Check to Check Reconciliation – Enduring Solution, to ensure future invoicing is correct first time Minor Release 16, approved by Change Management Committee on 8th April 2026 – Implementation Date is targeted for 12th June 2026
DSC Service Area Associated Funding Split | Service Area 4 : Meter Read/Asset processing
Proposed Funding split from Proposer | Delivery via Minor Release which is funded under existing DSC Service and Operate (S&O) costs.

## Slide 9: XRN 6081.B - Reconciliation of Multiple Read Replacements – Historic Reporting and Tactical Solution
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | 
This vote is to approve the change into development | 
Change Type | Non - Regulatory
Priority | Medium
Proposer | Xoserve
Change Proposal | Link to CP
Change Description | 
The coverage of this change proposal is around the reconciliation process and invoicing of this to Shipper Users. Where multiple Shipper readings, for the same MPRN, are submitted on the same date, they may not be correctly utilised within the reconciliation process e.g. a subsequent or replacement read submitted may be used rather than the first read received on the given day. This results in incorrect consumption calculations, inaccurate reconciliations, and incorrect invoicing. Currently, the process does not recognise, or order replacement reads submitted on the same date. As such, reconciliation is executed before later reads are factored in resulting in inaccurate calculations. | This applies to reads received via inbound read files: • UMR - Class 4 • UBR - Class 3 • RRP - RGMA replacement reads The objectives of this Change Proposal are to: 1. Review and analyse historic instances of the issue to allow for manual correction 2. Develop ongoing reporting to prevent inaccurate reconciliations from being included in customer invoices
DSC Service Area Associated Funding Split | Service Area 4 : Meter Read/Asset processing
Proposed Funding split from Proposer | Delivery via Minor Release which is funded under existing DSC Service and Operate (S&O) costs.

## Slide 10: XRN 6081.C - NDM Check to Check Reconciliation – Enduring Solution
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | 
This vote is to approve the change into development | 
Change Type | Non - Regulatory
Priority | Medium
Proposer | Xoserve
Change Proposal | Link to CP
Change Description
The coverage of this change proposal is around the reconciliation process and invoicing of this to Shipper Users. For Class 3 and 4 sites with Automated Meter Reading (AMR) equipment, Check to Check (C2C) reconciliation is performed when a site visit or RGMA actual read is received. This reconciliation must be based on the prevailing consumption which can be: • The deemed allocated position – The position calculated for the Commodity invoice with no subsequent reads, or • Actual consumption – Where readings exist, or • A combination of both - If readings exist but do not account for the full. C2C period Currently, the deemed allocated volume/energy, is always used as the prevailing position with existing readings not considered. The objective of this Change Proposal is to ensure that, during a C2C reconciliation the true prevailing volume position is used.
DSC Service Area Associated Funding Split | Service Area 4: Meter Read/Asset processing
Proposed Funding split from Proposer | Shipper 33% DNO 67%

## Slide 11: XRN 5994 – Emergency Contact Validation Service
Solution Option Change Pack Overview

## Slide 12: Change Summary
Solution Approach
The change requires the CDSP to provide a new Emergency Contacts Validation Service on behalf of the DNs to improve the quality of, and confidence in, the EMR data held on CDSP systems.
As part of this change there are two key objectives to be addressed:
The CDSP to produce a dataset for the ‘Top 200’ SMPs (by AQ) in each LDZ with an AQ above 732,000 kWh. This will be distributed to, and agreed with, the DNs. The CDSP will also produce and distribute two Quarterly reports post the contact validation period.
CDSP will also conduct a centralised call handling exercise on behalf of the DNs over a 4-month period to validate the data held on UK Link systems. The outcome of all the calls will be recorded and reported monthly to the respective DNs and Shippers.
This change is initially scoped as one-off ‘Prove Of Concept’, progressing to an enduring solution will be raised via a separate change request.
Notes: Add bullets

## Slide 13: To-Be Process
Reuse of current component/function
New component/function
1. Create Dataset of top 200 SMPs from UK Link
CDSP
Initial Dataset
Monthly Report for each month during call handling period
Quarterly Report for the periods following call handling period of top 200 SMPs from UK Link
2. Verify Dataset with the DNs
New Reports
DNs
Shippers
& DNs
4. Generate
Quarterly Reports against original dataset
One-off Solution
Call Handling Period Start
Dataset
1. Call each registered Emergency Contact at SMP site
2. Record call outcomes
3. Generate Monthly Report for call outcomes
Call Handling Period Ends
Shippers & DNs

## Slide 14: Solution Options
# | Description | Systems and process impacts | Cost Estimate Ranges
1 | Reports run in SAP BO and issued by Customer Ops. Calls made via a non-autonomous solution. | Reporting: Initial ‘Top 200’ report and subsequent 2 ‘Quarterly reports’ to be created and run in SAP BO. Monthly reports templates to be provided to and updated by Call Handlers, then reviewed and issued each month. All reports* to be issued via Customer Ops and to be password protected and distributed via email or huddle to all Shippers and DNs with one or more sites in the ‘Top 200’ portfolio. *For the Initial ‘Top 200 report’ this will only be issued to and reviewed by DNs. Call Handling: All calls to be made between a 4month consecutive period, calls to be manually undertaken and not via any automated call solution. A maximum of 3 call attempts will be made for each contact. | Delivery: £65k - £170k a. Onshore Call Handing. The is reflected by the top end of cost range. b. Offshore Call Handling This would be circa half the onshore cost.
2 | Reports run in SAP BO and issued via IX. Calls made via a non-autonomous solution. (Discounted) | Reporting: Initial ‘Top 200’ report and subsequent 2 ‘Quarterly reports’ to be created and run in SAP BO. Monthly reports templates to be provided to and updated by Call Handlers, then reviewed and issued each month. All reports* to be issued autonomously via IX to all Shippers and DNs with one or more sites in the ‘Top 200’ portfolio. *For the Initial ‘Top 200 report’ this will only be issued to and reviewed by DNs. Call Handling: All calls to be made between a 4month consecutive period, calls to be manually undertaken and not via any automated call solution. A maximum of 3 call attempts will be made for each contact. Discounted: (Updated 08/05/2026) This has been discounted for the ‘Proof Of Concept’ due to increased costs and potential for the reports not to reach the correct internal parties. | Delivery: £100k – £210k (Dependant on location of call handling)

## Slide 15
SECTION 3:
Detailed Design
03
3a. Design Considerations
3b. Requirements Clarification
Project Updates

## Slide 16
SECTION 3:
Detailed Design
3a.i XRN 5937.3 - Facilitating Bi-Directional Connections Between IGT pipelines
3a.ii XRN 6081.C - NDM Check to Check Reconciliation – Enduring Solution
3a. Design Considerations
3b. Requirements Clarification
None for this meeting

## Slide 17
3a.i XRN 5937.3 - Facilitating Bi-Directional
Connections Between IGT pipelines
Link to Change Pack

## Slide 18: XRN6081.C - NDM Check to Check Reconciliation – Enduring Solution
Detailed Design Overview
May 2026

## Slide 19: Change Background
Problem Statement : For Class 3 and 4 sites with Automated Meter Reading (AMR) equipment, Check to Check (C2C) reconciliation is performed when a site visit or RGMA actual read is received. This reconciliation must be based on the prevailing consumption which can be:
  The deemed allocated position – The position calculated for the Commodity invoice with no subsequent reads, or
  Actual consumption – Where readings exist, or
  A combination of both - If readings exist but do not account for the full. C2C period
Currently, the deemed allocated volume/energy, is always used as the prevailing position with existing readings not considered.
Consequence : As a result, the Check Read energy is being prorated using an estimated consumption profile rather than the most recent or actual consumption profile. This can lead to incorrect charges invoiced to customers.
Mitigation in place : Currently, a manual workaround is in place to address queries raised by shippers. The CDSP Operations team recalculates reconciliation values on a case-by-case basis and creates a consumption adjustment using revised volumes. This process requires manual review to be completed by the Shipper, to identify inconsistencies and raise them, and then manual effort by CDSP resource to execute the workaround.
The workaround will be superseded with the solutions implemented as part of related change XRN6081.A, which will enable CDSP to identify anomalies and resolve them via the adjustment processes prior to invoice run. This change, will resolve the functional calculation issues within the system and remove any need for adjustments going forward.

## Slide 20: Detailed Design Summary
Change Scope:
  Enhancements to be made to the Class 3 and Class 4 C2C reconciliation processes, to ensure they utilise the latest prevailing volume
  In addition, the Class 3 and Class 4 C2C reconciliation process will be updated to calculate a revised reconciliation factor across the full C2C period, based on the latest prevailing volume
    Where the actual prevailing volume is zero, the deemed volume will be used, in this calculation, for the relevant period. This is in line with existing BAU rules implemented as part of XRN5007 - Correction in the Reconciliation process where the volume is zero
  As a result, the correct outputs from the C2C reconciliation process will feed into the Reconciliation billing calculations as per the existing BAU rules for determining the charges that are invoiced through the monthly amendments invoice and ensure compliance with UNC Section E6.2
While XRN6081.C addresses the root cause of the issue, related change XRN6081.A – “Fix Historic NDM Check to Check Reconciliation Periods - Tactical Solution” will seek to identify the historic impacted C2C reconciliations and issue a correction to the respective customers. This will include a tactical solution to correct C2C reconciliations in lieu of XRN6081.C implementation.
XRN6081.A has been approved into the scope of Minor Release 16 and has a planned implementation date in July 2026.

## Slide 21: Next Steps
The Detailed Design Change Pack (DDCP) was issued for consultation on 18th May 2026, due to close out 2nd June 2026
  Change pack can be found here
Shippers and DNOs will vote on the outcome of the DDCP consultation at ChMC on 10th June 2026.

## Slide 22
Thank you!
Any questions?

## Slide 23
Section 4: Release/Project Updates
04
4a. Minor Release 16 Scope
4c. XRN 6045 June 26 Major Release
4b. XRN 5983 Feb 26 Major Release

## Slide 24: XRN6065 – Minor Release 16 - Status Update
RAG Status | Overall Project RAG status |  | 
 | Schedule0 | Risks and Issues | Costs
 | Status Justification |  | 
Schedule | The scope of Minor Release 16 was presented for approval at the ChMC meeting on 08/04/26. Overall release is tracking at risk; Build projected to be completed on 01/05/26. Test preparation in progress, currently Amber due to BP24 Sustain delays moving environments delaying the start of ST. Progress Update: XRN 6081A Build completion in progress and is in Testing. Decision in May ChMC: None | Implementation date July 2026 | 
Risks and Issues | Deferred Sustain implementation date will result in MiR 16 implementation dates being pushed back. Replan is being worked on to move Implementation date to July 26. |  | 
Costs | UK Link costs covered under Service and Operate funding |  | 
Scope | XRN 6081A – Meter Reading Service Improvement A - Fix Historic NDM Check to Check Reconciliation Periods - Tactical Solution |  | 
Complete
On Track
At Risk
Overdue

## Slide 25: XRN5983 – February 26 Major release - Status Update
RAG Status | Overall Project RAG status |  | 
 | Schedule0 | Risks and Issues | Costs
 | Status Justification |  | 
Schedule | The scope of February 26 Major Release was presented for approval at the ChMC meeting on 10/09/25. Overall release is tracking to target. Project was successfully implemented, 27/02/26, Post Implementation Support expected to complete 10/05/26. Progress Update: XRN5906, 5872, 5914/5922 are in Post implementation support (PIS) PIS and First usage is progressing to plan. | Implementation date 27th February, contingency date 6th March | 
Risks and Issues | N/a |  | 
Costs | Changes are currently delivering with projected costs. |  | 
Scope | XRN5906 - Extending the PC4 Read Submission Window. XRN5872 - Updates to the AQ Amendments Process. XRN5914/XRN5922 - Shorten of the current LIS (Line in sand) date to 2-3 years & amend the LIS to rolling Period. |  | 
Complete
On Track
At Risk
Overdue

## Slide 26: XRN6045 – June 26 Major Release- Status Update
RAG Status | Overall Project RAG status |  | 
 | Schedule0 | Risks and Issues | Costs
 | Status Justification |  | 
Schedule | The scope of June 26 Major Release was presented for approval at the ChMC meeting on 11/02/2026. Overall release is tracking to target; project is planned implement on 26/06/2026. Progress Update: June is tracking at Amber due to delays and dependencies on Sustain 24. Work is ongoing on a replan to ensure the implementation date is not affected by these delays. XRN5805 has started Build as per plan on the 13/04/26 XRN5702 started Build as per plan on the 30/03/26 and is due to start ST once the dependencies from Sustain 24 have been removed. Decision in April ChMC: None | Implementation date 26th June 2026, contingency date 3rd July 2026 | 
Risks and Issues | N/A |  | 
Costs | Forecast to complete delivery against approved BER |  | 
Scope | XRN5702 – Update to assess the replacement of Facsimile as a form of communication (Modification 0864S) XRN5805 - Alternative Solution to address instances where VBA macros are present in DN Templates |  | 
Complete
On Track
At Risk
Overdue

## Slide 27
Section 5:
Change Pipeline
05
Change Pipeline

## Slide 28: 2026 Forward View - Change Delivery Plan
January 26 – December 2026
Jan-26
June-26
February 26 – Major Release (XRN5983)
XRN5872 | XRN5906 | XRN5914 | XRN5922
March-26
Sep-26
Dec-26
June 26 – Major Release (XRN6045)
XRN5702 |XRN5805
Slide produced 29h July 2025
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative / Target Implementation Date – Changes are planned for delivery – Funding not yet approved by ChMC
= Implemented Change / Release
November 26 - Major Release
XRN5940| Meter Read Service Improvements (Part C)
XRN5994 - Emergency Contact Data Service
Identifying Improvements to Meter Point Location Address Data Processes
XRN5968 | XRN5546
Minor Release 18
MiR17 - Service Improvements Part B
MiR16 – MR Service Improvements Part A
PIX
5924
XRN5941 – Performance Assurance Committee - Audit PAT
XRN6041 - CDSP Obligations required for the introduction of the Gas Shipper Obligation

## Slide 29: Change Delivery Plan – January 2026 – December 2026
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Delivery Date | Release Type | Firm / Indicative
5872 | Mod0876S Updates to the Annual Quantity (AQ) amendment process | SEFE | Shipper DN | Shipper | £190k | 27 February 2026 | Major | Firm
5906 | Mod0884 – Extending the PC4 Read Submission Window | OVO | Shipper DN IGT | Shipper DN | £105k | 27 February 2026 | Major | Firm
5914 5922 | Mod0886 - Amend the Code Cut-Off Date to a Rolling Period Mod0896 – Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years | SSE SEFE | Shipper DN IGT | Shipper | £90k | 27 February 2026 | Adhoc / Major | Firm
5941 | Performance Assurance Committee – Audit PAT | Xoserve | Shipper DN IGT | Shipper DN IGT | £300K | TBC | Adhoc | Indicative
5994 | Emergency Contact Validation Service | Cadent | Shipper DN | tbc | TBC | May 2026 | Adhoc | Indicative
5702 | Mod0864S - Update to assess the replacement of Facsimile as a form of communication | NGT | All DSC Customers | Shipper DN | £158k | 26 June 2026 | Major | Firm
5805 | Alternative Solution to address instances where VBA macros are present in DN Templates | WWU | DN | DN | £160k | 26 June 2026 | Major | Firm
5924 | Physical Information Exchange (PIX) Ongoing Support Options | Xoserve | All | TBC | N/A | 31 June 2026 | Adhoc | Firm
6081 A | Meter Read Service Improvements Part A Fix Historic NDM Check to Check Reconciliation Periods - Tactical Solution | Xoserve | Shipper DN | N/A | N/A | July 2026 | Minor | Indicative
6081 B | Meter Read Service Improvements Part B Reconciliation of Multiple Read Replacements – Historic Reporting and Tactical Solution | Xoserve | Shipper DN | N/A | N/A | September 2026 | Minor | Indicative
5949 | New Priority Consumer Category related to Community Heating (Phase 1) | NGT | All DSC Customers | TBC | TBC | September 2026 | Adhoc | Indicative
5940 | Mod0890 – Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation | Centrica | Shipper DN | TBC | £270k | 6 November 2026 | Major | Indicative
6081C | Meter Read Service Improvements – Part C NDM Check to Check Reconciliation – Enduring Solution | Xoserve | Shipper DN | Shipper DN | £110K | 6 November 2026 | Major | Indicative
6041 | UNC Modification 0922 (IGT UNC Modification 180) – CDSP Obligations required for the introduction of the GSO | CDSP | ALL DSC Parties | Shipper | TBC | December 2026 | Adhoc | Indicative

## Slide 30: Change Backlog – Priority Service Changes ‘In Progress’
XRN | Change Title | Proposer | Benefit / Impact | Funding | Status | May 26 - ChMC Update
6001 | Modification 0909 - Refining the Class 2 Individual Valid Meter Reading Requirement Performance Measures | SEFE | Shipper DN | Shipper DN | Requirements | Change Proposal created to enable CDSP solution to be progressed in adherence to the related UNC Modification
6000 | Modification 0908 – Removal of DNO meter reading obligations resulting from non-provision of a Valid Meter Reading by a Shipper | WWU | Shipper DN IGT | DN | Requirements | Change Proposal created to enable CDSP solution to be progressed in adherence to the related UNC Modification which has been approved.
5972 | CDSP provisions to support new Supplier Deed of Undertaking (DoU) Licence Condition (9a) | Cadent | DN IGT | DN | Requirements | Change Proposal raised on behalf of DNs to ensure new Deed of Undertaking arrangements are put in place with Supplier organisations. Analysis on Invoicing processes (charge types) to be performed and validated with DNs.
5987 | Modification 0915 – Debt Relief Scheme Payment (DRSP) | NGN | Shipper DN IGT | NGT DN | Requirements | CDSP will be actively supporting Modification development over proceeding months ahead of baselining requirements.
6079 | UNC 0926S Maintenance criteria for Emergency Contact data held in Central Systems | Cadent | Shipper DN IGT | Shipper DN | Requirements | Change Proposal created to enable CDSP solution to be progressed in adherence to the related UNC Modification
6067 | Facilitating Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression (Modification 0894) | Cadent | Shipper DN NGT | TBC | Requirements | Change Proposal created to enable CDSP solution to be progressed in adherence to the related UNC Modification
6066 | Facilitating Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression (Modification 0894A) | National Gas Transmission | Shipper DN NGT | TBC | Requirements | Change Proposal created to enable CDSP solution to be progressed in adherence to the related UNC Modification

## Slide 31: Change Backlog – Remaining Changes ‘In Progress’
XRN | Change Title | Proposer | Benefit / Impact | Funding | Status | May 26 - ChMC Update
5473 | Meter Asset Comparison Service | CDSP | Shipper | Shipper | Solution Assessment | Issued out for consultation – preferred option will be progressed through the relevant delivery path (e.g. DDP Release)
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Solution Assessment | Solution Option issued for consultation in May ‘25 Change Pack – next steps to be confirmed following change pack decision and agreement on how to progress.
5810 | Theft of Gas (ToG) DN Calculation Tool | Cadent | DN | DN | Solution Assessment | Protype solution being trialled with one DN party ahead of finalising functionality and sharing with all DN parties. Workshop arranged 3rd October. Continue to monitor progress with DNs before reaching agreement that change can be closed.
5950 | DSC Invoice Number generation review | CDSP | Shipper DN NGT | TBC | Solution Assessment | Re-assigned to change backlog as change is not time critical and will require customer notification period prior to delivery. Solution Option Change Pack targeted in June.
5955 | Private networks duplicate MPRNs - options for long-term fix | Cadent | DN | DN | Solution Assessment | Re-assigned to change backlog ahead of Solution Option Change Pack being published in May for consultation.
5968 | Identifying improvements to Meter Point Location Address Data processes | Cadent | DN | DN | Analysis | Parent Change Proposal raised to perform analysis and make recommendations on changes that can be implemented to the Address Amendment process.
6039 | Provision of IGT SMP Data to DNs | NGN | DN IGT | DN | Requirements | Change Proposal raised to progress solutions that enable DNs the ability to receive IGT SMP data.
6056 | Introduction of new Supply Meter Point status of ‘IS’ (Isolation) - Cleanse and remove obsolete ‘CL’ (Clamped) status | Cadent | DN IGT Shipper | DN | Requirements | New Change Proposal raised to progress solution that enables DNs and other industry stakeholders the ability to acknowledge a Supply Meter Point Status of Isolation.

## Slide 32: Change Backlog – ‘On Hold’ Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | May 26 ChMC Update
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | *£260k revised following design | Agreed following August bi-party CSEP meeting that change will remain on hold whilst data cleansing activities were progressed.
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | N/A | N/A – performing analysis on data extracts provided by DCC Incorporate findings into Address Management Project (XRN5968)
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | TBC | Low Priority – CDSP raised Change Proposal
5701 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert (Modification 0843 / IGT 165) | OVO | Shipper DN IGT | DN IGT | TBC | Withdrawn following Ofgem’s decision to reject UNC Modification 0843 ¦ IGT165
5806 | CDSP Solution to enable exit of application of User Premises Termination Notice (UPTN) | NGT | All DSC Customers | TBC | TBC | Change Proposal raised to analyse process and solution impacts that may be necessary to facilitate exit – analysis being planned in with relevant resource

## Slide 33: DSC Change Pack Consultation Plan (two-month view)
May – 26
June - 26
July – 26
XRN5955 - Private networks duplicate MPRNs - options for long-term fix
Key
= Design Change Pack for Consultation
= Solution Option Change Pack for Consultation
= For Information Change Pack
XRN5950 - DSC Invoice Number generation review
XRN5940 - Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (Modification 0890)
XRN5937.3 - Facilitating Bi-Directional Connections Between IGT pipelines and the NTS (Modification 0887)
XRN6081.C - NDM Check to Check Reconciliation – Enduring Solution

## Slide 34
Section6: AOB
06
Smart Read Selection from SEC Message

## Slide 35
Section 7:
Annex
07
7a. ChMC Update
7b. Rec Update
7c. POAP