## Slide 1: XRN5533 – February 23 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, UK Link user testing phase completed on 08/12 as per plan. Currently on track to complete regression testing phase 19/01 Progress update: User acceptance testing complete on 08/12 Regression testing in progress, on track to complete on 19/01 DDP build for XRN4990 in progress, delivery on track to complete by 20/01 DDP testing for XRN4990 in progress, on track to complete by 21/02 Decision in January ChMC: None |  | Implementation date of 25th February; with a contingency implementation date of 4th March | 
Risks and Issues | There is a risk that the solution being delivered under XRN5298 may not work as expected at the point SGN go live with the H100 project. Due to a significant gap between XRN5298 being delivered as part of the Feb 23 release, and the date at which the H100 project itself is scheduled to go live Update – SGN have confirmed that Q4 2024 is when the first H100 connections will go live. Discussions underway regarding options for carrying out additional regression testing closer to the H100 go live |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN4900 - Biomethane/Propane Reduction XRN4978 - Shipper - Notification of Rolling AQ Value XRN4989B - Residual AMT activities XRN4990 - MOD0664 – Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 XRN4992B - MOD0797 - Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process XRN5298 - H100 Fife Project – Hydrogen Network Trial |  |  | 
Slide updated on 20th December 2022
Complete
On Track
At Risk
Overdue